## Quarterly Plan
Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4
Week | Application | Week | Application | Week | Application | Week | Application
2022-01-08 |  | 2022-04-03 | Deploy locally | 2022-07-03 | Setup Continuous Delivery | 2022-10-02
2022-01-16 |  | 2022-04-10 | Test Application | 2022-07-10 |  | 2022-10-09 | Bussiness Application Onwer Testing
2022-01-23 | Draft Functional Spec | 2022-04-17 |  | 2022-07-17 |  | 2022-10-16
2022-01-30 | Create Github Repo | 2022-04-24 | Continuous Integration - Break Fixes | 2022-07-22 |  | 2022-10-23
2022-02-06 |  | 2022-05-01 |  | 2022-07-31 |  | 2022-10-30
2022-02-13 | Clone Repo to Azure | 2022-05-08 |  | 2022-08-07 | Test CD | 2022-11-06 | Business Users Test
2022-02-20 | Start Building Application | 2022-05-15 |  | 2022-08-14 |  | 2022-11-13
2022-02-27 |  | 2022-05-22 |  | 2022-08-21 |  | 2022-11-20
2022-03-06 |  | 2022-05-29 |  | 2022-08-28 |  | 2022-11-27 | Continuous Delivery - Break Fixes
2022-03-13 |  | 2022-06-05 | Setup Continuous Integration | 2022-09-04 | Application Ready for Dev/QA | 2022-12-04 | Deploty to Prod if Testing Ok
2022-03-20 |  | 2022-06-12 | Build Actions | 2022-09-11 |  | 2022-12-11
2022-03-27 |  | 2022-06-19 |  | 2022-09-18 |  | 2022-12-18
|  | 2022-06-26 | Test CI | 2022-09-25 |  | 2022-12-25
| Goals |  | Goals |  | Goals |  | Goals
| Design Completed |  | Test the Application |  | Set Up Azure Pipelines |  | Test the application by Owner and Business Users
| Phase#1 of Application |  | Set up Continous Integration |  | Test the Continuous Delivery Pipeline |  | Complete any break fixes
|  |  | Test the Build Action Workflows |  | Ready app for Dev/QA |  | Deploy application to the Production Environment